## Work Breakdown
Deliverable | Task | Estimate | Priority | Deliverable | Task | Estimate | Priority | Deliverable | Task | Estimate | Priority | Deliverable | Task | Estimate | Priority | Total Estimate
Creation of Pages |  | 7 |  | Functions Validation |  | 11 |  | Design |  | 4 |  | Testing |  | 1 |  | 23
| Login Page | 1 | M |  | User login validation | 1 | M |  | Designing layout Login page | 0.5 | M |  | Testing the whole web application | 1 | S
| Sign up Page | 1 | M |  | User logout validation | 1 | M |  | Designing layout Sign up form | 0.5 | M
| Home Page | 1 | M |  | Sign up form validation | 1 | M |  | Designing Header and Footer | 0.5 | M
| Projects Page | 1 | M |  | Form of projects creation | 1 | M |  | Designing layout Home page | 0.5 | M
| Registration Page | 1 | M |  | Projects deletion | 0.5 | M |  | Designing layout Projects page | 0.5 | M
| Teams Page | 1 | M |  | Projects edition | 0.5 | S |  | Designing layout Registration page | 0.5 | M
| Events Page | 1 | M |  | Projects saving | 0.5 | M |  | Designing layout Teams page | 0.5 | M
[5 empty] | User registration validation | 1 | M |  | Designing layout Events page | 0.5 | M
[5 empty] | Teams creation | 0.5 | M
[5 empty] | Teams deletion | 0.5 | M
[5 empty] | Teams edition | 0.5 | S
[5 empty] | Events creation | 0.5 | M
[5 empty] | Events deletion | 0.5 | M
[5 empty] | Events edition | 0.5 | S
[5 empty] | Events saving | 0.5 | M
[5 empty] | Show up User Credentials in the top Bar | 1 | M
Note on C1: Days
Note on D1: MoSCoW

## Gantt Chart
Publishing House Web Application
Legend |  | TO DO | IN PROGRESS | DONE
Project Start | 2021-02-22
Project End | 2021-04-20
|  |  | February | [12 empty] | March | [27 empty] | April
Deliverable | Task | Estimate | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Total |  | 23
Creation of Pages |  | 7
Login Page |  | 1
Sign up Page |  | 1
Home Page |  | 1
Projects Page |  | 1
Registration Page |  | 1
Teams Page |  | 1
Events Page |  | 1
Functions Validation |  | 11
User login validation |  | 1
User logout validation |  | 1
Sign up form validation |  | 1
Form of projects creation |  | 1
Projects deletion |  | 0.5
Projects edition |  | 0.5
Projects saving |  | 0.5
User registration validation |  | 1
Teams creation |  | 0.5
Teams deletion |  | 0.5
Teams edition |  | 0.5
Events creation |  | 0.5
Events deletion |  | 0.5
Events edition |  | 0.5
Events saving |  | 0.5
Show up User Credentials in the top Bar |  | 1
Design |  | 4
Designing layout Login page |  | 0.5
Designing layout Sign up form |  | 0.5
Designing Header and Footer |  | 0.5
Designing layout Home page |  | 0.5
Designing layout Projects page |  | 0.5
Designing layout Registration page |  | 0.5
Designing layout Teams page |  | 0.5
Designing layout Events page |  | 0.5
Testing |  | 1
Testing the whole web application |  | 1